## Important dates
No. | Date | Title | Type | Progress | Note
1 | 2023-10-13 | Agreed Project Brief | Deadline | 100% | SUBMIT a one-page PDF
2 | 2023-11-13 | ELEC3227 CW | Event | 100% | CW Review meeting (standard document)
3 | 2023-12-11 | ELEC3227 CW | Event | 0% | PRESENT Embedded Network Coursework demo
4 | 2023-12-12 | Progress Report | Deadline | 0% | SUBMIT a max 3000 words pdf
| 2024-01-08 | ELEC3227 CW | Event | 0% | SUBMIT written project report
5 | 2024-04-30 | Final Project Report | Deadline | 0% | SUBMIT final report and related files
6 | 2024-05-16 | Project Viva | Event | 0% | PRESENT project demo
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## Planned
Project Management Gantt Chart | Color Code | Orange: Report related | Green: Hardware related |  | Blue: Software related |  |  | p1 refers to phase 1
Tasks | Start Date | Expected Duration (days) | End Date | Progress | Done? | Notes
Literature research | 2023-10-02 | 10 | 2023-10-12 | 100% | Yes | Google scholar, IEEE papers, related projects etc
Revise Project Brief v1 | 2023-10-02 | 3 | 2023-10-05 | 100% | Yes | Email new revised project brief when done, check samsung notes annotations | Done v2
Software prototype research p1 (SPR1) | 2023-10-02 | 2 | 2023-10-04 | 100% | Yes | GoDot first, then Unity, check simple way to get SBS video player and environment | RancidMilkGames/Godot-VLC: An example Godot 4 project demonstrating integration with libVLCSharp (github.com)
Software prototype development p1 (SPDEV1) | 2023-10-04 | 3 | 2023-10-07 | 100% | Yes
Software prototype test p1 (SPT1) | 2023-10-06 | 2 | 2023-10-08 | 100% | Yes
Hardware prototype research p1 (HPR1) | 2023-10-08 | 2 | 2023-10-10 | 100% | Yes | read, and download all related specs and datasheet and put into a folder
Hardware prototype documentation p1 (HPDOC1) | 2023-10-10 | 2 | 2023-10-12 | 100% | Yes | Write down related thing into design document and thoughts
Design document drafting p1 (DD1) | 2023-10-12 | 3 | 2023-10-15 | 100% | Yes | finalise initial design and feasibility to start get hardware
Draft Project Report | 2023-10-13 | 2 | 2023-10-15 | 100% | Yes | Start drafting on latex
Hardware procurement | 2023-10-16 | 14 | 2023-10-30 | 100% | Yes | submit request and wait till get component
SPR2: Stereo and OpenXR implementation | 2023-10-17 | 7 | 2023-10-24 | 100% | Yes
Software prototype documentation (SPDOC1) | 2023-10-24 | 7 | 2023-10-31 | 100% | Yes
SPDEV2: Stereo image and video | 2023-10-19 | 14 | 2023-11-02 | 0% | 0
SPT2: Stereo 3DS video and image test | 2023-11-02 | 3 | 2023-11-05 | 100% | Yes
Embedded Hardware Programming study | 2023-11-05 | 7 | 2023-11-12 | 100% | Yes | Learn embedded programming for rasp pi pico and related interfaces for components im using
Hardware prototype development (HPDEV1): Basic Mono Functions | 2023-11-12 | 14 | 2023-11-26 | 100% | Yes | Get the basic implementation working (camera picture, video, audio and sdcard support) mono camera for now, then test with signal (control pico)
Hardware prototype testing (HPT1): Mono Testing | 2023-11-26 | 3 | 2023-11-29 | 0% | 0 | Try leave the pico plugged in/battery powered test and see timelapse create (mono)
HPDOC2: Reflections and problems faced | 2023-11-29 | 2 | 2023-12-01 | 0% | 0
SPDEV3: Image timelapse browsing (mono) and video playback (UI) | 2023-12-01 | 14 | 2023-12-15 | 0%
SPT3: Pico Camera images and video test (resolution changes) | 2023-12-15 | 3 | 2023-12-18 | 0%
HPR2: 3D Modelling Software Study and training | 2023-12-20 | 14 | 2024-01-03 | 0%
HPDEV2: 3D model design v1 | 2024-01-03 | 5 | 2024-01-08 | 0%
EXAM WEEKS | 2024-01-08 | 21 | 2024-01-29 |  |  | If 3d model design not yet done, can use the remaining exam weeks day
HPDEV3: Stereo camera functionality | 2024-01-29 | 14 | 2024-02-12 |  |  | might still uses powerbank for power at this point, unless dev is faster
HPT3: Functional hardware test to get footage | 2024-02-05 | 7 | 2024-02-12 |  |  | in tandem in case problems occus midway
SPDEV3: Stereo audio sync and optimisation | 2024-02-12 | 7 | 2024-02-19
SPT3: Testing on friends for feedback | 2024-02-19 | 3 | 2024-02-22
HPDEV4: Add onboard battery (and charging circuit) | 2024-02-22 | 10 | 2024-03-03
HPT4: Test onboard battery life and powermode | 2024-03-03 | 7 | 2024-03-10
Optimisation and organisation | 2024-03-10 | 5 | 2024-03-15
Final report write up | 2024-03-15 | 21 | 2024-04-05
0
0
0
0
0
0
0
0
0
Formulas:
Green: Hardware related = [Color Code]+[Orange: Report related]

## Executed
Project Management Gantt Chart | Color Code | Orange: Report related | Green: Hardware related |  | Blue: Software related |  |  | p1 refers to phase 1
Tasks | Start Date | Actual Duration (days) | End Date | Progress | Done? | Notes
Literature research | 2023-10-02 | 14 | 2023-10-16 | 100% | Yes | Got lots of interesting ideas, inspirations and methodologies from some papers, but cant really replicate them for my use case..
Revise Project Brief v1 | 2023-10-02 | 6 | 2023-10-08 | 100% | Yes
Software prototype research p1 (SPR1) | 2023-10-02 | 7 | 2023-10-09 | 100% | Yes | https://youtu.be/snqoqgQy3Uk | https://youtu.be/dFw8itaoDiU | Do Godot 4 have inbuilt VR video (SBS/3D) player built in? : godot (reddit.com)
Software prototype development p1 (SPDEV1) | 2023-10-04 | 5 | 2023-10-09 | 100% | Yes | Done VR screen video player like utube tutorial above but no stereo implementation yet
Software prototype test p1 (SPT1) | 2023-10-06 | 3 | 2023-10-09 | 100% | Yes | Tested conversion of mp4 to .ogg with ffmpeg
Hardware prototype research p1 (HPR1) | 2023-10-08 | 4 | 2023-10-12 | 100% | Yes | Most likely a combination of 3 raspberry pi pico W, 1 for control and sync, 2 for hosting arducam, microphone and sdcard
Hardware prototype documentation p1 (HPDOC1) | 2023-10-11 | 4 | 2023-10-15 | 100% | Yes | Download all related specs and datasheet to a folder. | Not Downloaded but have all em links on design document
Design document drafting p1 (DD1) | 2023-10-15 | 1 | 2023-10-16 | 100% | Yes | What's the correct way to power one pi pico using another? : raspberrypipico (reddit.com)
Draft Project Report | 2023-10-16 | 1 | 2023-10-17 | 100% | Yes
Hardware procurement | 2023-10-16 | 7 | 2023-10-23 | 100% | Yes | Ordered, waiting to collect
Learning LaTeX | 2023-10-18 | 14 | 2023-11-01 | 100% | Yes | Just use Overleaf bro
SPR2: Stereo and OpenXR implementation | 2023-10-17 | 18 | 2023-11-04 | 100% | Yes | Fallback solutions: Skybox VR, SteamVR video player etc | IT WORKS, ASKED QUESTION IN #XR channel in godot discord and kind malcolm nixon gave me:https://github.com/Malcolmnixon/godot-stereo-video
Software prototype documentation (SPDOC1) | 2023-10-24 |  | 2023-10-24
SPDEV2: Stereo image and video | 2023-10-19 | 16 | 2023-11-04 | 100% | Yes | IT WORKS, ASKED QUESTION IN #XR channel in godot discord and kind malcolm nixon gave me:https://github.com/Malcolmnixon/godot-stereo-video
SPT2: Stereo footage video and image test | 2023-11-02 | 3 | 2023-11-05 | 100% | Yes | Used test footage from example, also learned how to install and use yt-dlp if I need to get more footage for testing
Embedded Hardware Programming study | 2023-11-05 | 10 | 2023-11-15 | 100% | Yes | FKED ONE OF PICO BY SHORTING IT USING MULTIMETER TO CHECK 3.3V while its running smh
Hardware component testing | 2023-11-08 | 8 | 2023-11-16 | 30% | No | GOT the SPI_CAMERA_DEMO WORKING FINALLY. THE PROBLEM IS PROVIDED WIRE JUMPER SUCKS< the connection is unstable, some don’t even have proper crimp as the copper exposed rusted…
ELEC Coursework and procrastination (reading and VR playing for research) | 2023-11-16 | 6 | 2023-11-22 | 100% | Yes
Progress Report Writeup | 2023-11-24 | 3 | 2023-11-27 | 20%
Hardware prototype development (HPDEV1): Basic Mono Functions | 2023-11-12 | 0 | 2023-11-12
Hardware prototype testing (HPT1): Mono Testing | 2023-11-26 |  | 2023-11-26
HPDOC2: Reflections and problems faced | 2023-11-29 |  | 2023-11-29
SPDEV3: Image timelapse browsing (mono) and video playback (UI) | 2023-12-01 |  | 2023-12-01
SPT3: Pico Camera images and video test (resolution changes) | 2023-12-15 |  | 2023-12-15
HPR2: 3D Modelling Software Study and training | 2023-12-20 |  | 2023-12-20
HPDEV2: 3D model design v1 | 2024-01-03 |  | 2024-01-03
EXAM WEEKS | 2024-01-08 |  | 2024-01-08
HPDEV3: Stereo camera functionality | 2024-01-29 |  | 2024-01-29
HPT3: Functional hardware test to get footage | 2024-02-05 |  | 2024-02-05
SPDEV3: Stereo audio sync and optimisation | 2024-02-12 |  | 2024-02-12
SPT3: Testing on friends for feedback | 2024-02-19 |  | 2024-02-19
HPDEV4: Add onboard battery (and charging circuit) | 2024-02-22 |  | 2024-02-22
HPT4: Test onboard battery life and powermode | 2024-03-03 |  | 2024-03-03
Optimisation and organisation | 2024-03-10 |  | 2024-03-10
Final report write up | 2024-03-15 |  | 2024-03-15
Formulas:
Green: Hardware related = [Color Code]+[Orange: Report related]

## Combined
Project Management Gantt Chart | Color Code | Orange: Report related | Green: Hardware related |  | Blue: Software related | p1 refers to phase 1
Tasks | Start Date | Expected Duration (days) | Actual Duration | Difference
Literature research | 2023-10-02 | 10 | 14 | 4
Revise Project Brief v1 | 2023-10-02 | 3 | 6 | 3
Software prototype research p1 (SPR1) | 2023-10-02 | 2 | 7 | 5
Software prototype development p1 (SPDEV1) | 2023-10-04 | 3 | 5 | 2
Software prototype test p1 (SPT1) | 2023-10-06 | 2 | 3 | 1
Hardware prototype research p1 (HPR1) | 2023-10-08 | 2 | 4 | 2
Hardware prototype documentation p1 (HPDOC1) | 2023-10-11 | 2 | 4 | 2
Design document drafting p1 (DD1) | 2023-10-15 | 3 | 1 | 0