## Planned
Project Management Gantt Chart
Tasks | Start Date | Expected Duration (days) | End Date | Progress | Done? | Notes
Literature research | 2023-10-02 | 10 | 2023-10-12 | 40% | No | Google scholar, IEEE papers, related projects etc
Revise Project Brief | 2023-10-02 | 3 | 2023-10-05 | 20% | No | Email new revised project brief when done, check samsung notes annotations
Software prototype research | 2023-10-02 | 2 | 2023-10-04 | 80% | No | GoDot first, then Unity, check simple way to get SBS video player and environment | RancidMilkGames/Godot-VLC: An example Godot 4 project demonstrating integration with libVLCSharp (github.com)
Software prototype development | 2023-10-04 | 3 | 2023-10-07 | 10% | No
Software prototype test | 2023-10-06 | 2 | 2023-10-08 | 0% | No
Hardware prototype research | 2023-10-08 | 2 | 2023-10-10 | 0% | No
Hardware prototype documentation | 2023-10-10 | 2 | 2023-10-12 | 0% | No
Design document drafting | 2023-10-13 | 5 | 2023-10-18 | 0% | No
Formulas:
End Date = [Start Date]+[Expected Duration (days)]

## Executed
Project Management Gantt Chart
Tasks | Start Date | Actual Duration (days) | End Date | Progress | Done? | Notes
Literature research | 2023-10-02 | 3 | 2023-10-05 | 40% | No
Revise Project Brief | 2023-10-02 | 3 | 2023-10-05 | 20% | No
Software prototype research | 2023-10-02 | 3 | 2023-10-05 | 80% | No | https://youtu.be/snqoqgQy3Uk | https://youtu.be/dFw8itaoDiU | Do Godot 4 have inbuilt VR video (SBS/3D) player built in? : godot (reddit.com)
Software prototype development | 2023-10-04 | 1 | 2023-10-05 | 10% | No
Software prototype test | 2023-10-06 |  | 2023-10-06 | 0% | No
Hardware prototype research | 2023-10-08 |  | 2023-10-08 | 0% | No
Hardware prototype documentation | 2023-10-10 |  | 2023-10-10 | 0% | No
Design document drafting | 2023-10-13 |  | 2023-10-13 | 0% | No
0
Formulas:
End Date = [Start Date]+[Actual Duration (days)]